## Task Allocation
User Story / Reference | Task | Assigned to | Start date | Completion date
Shared
Shared — all three | Schema design and schema.sql review | All
Person 1 — Auth, Admin & News Backend
Setup | Flask app setup and project structure | Person 1
US-01 | Auth routes — register, login, session | Person 1
US-14 | Admin metrics route | Person 1
E-05 / E7 | News cache table and /api/news/:ticker Flask route | Person 1
E7 | Anthropic SDK integration | Person 1
US-01 | Login and signup HTML/CSS pages | Person 1
E7 | AI news summary panel UI | Person 1
US-02 / US-03 / US-13 | Holdings table in MySQL — create, read, update, delete | Person 2
Person 2 — Portfolio & Transactions
US-02 / US-03 / US-13 | Holdings CRUD Flask routes | Person 2
US-10 | Transaction history route and MySQL queries | Person 2
US-05 | Alpha Vantage price fetching route | Person 2
US-04 | Dashboard page — total value, daily change, P&L | Person 2
US-07 | Holdings table UI with sorting | Person 2
US-13 | Edit/delete transaction UI | Person 2
E-05 | News cache MySQL queries and schema | Person 3
Person 3 — News, Search & Charts
US-06 / US-09 | News feed Flask routes | Person 3
US-11 | Watchlist MySQL table and routes | Person 3
US-08 | Allocation chart UI and calculation logic | Person 3
US-06 / US-09 | News feed page with ticker filter | Person 3
US-12 | Stock detail page with news panel | Person 3
US-11 | Search bar UI and watchlist display | Person 3

## Summary
Person | Responsibilities | Tasks
Person 1 | Auth, Admin & News Backend Flask setup, auth routes, admin, news API, Anthropic SDK, login UI, AI summary panel | 8
Person 2 | Portfolio & Transactions Holdings CRUD, transaction history, Alpha Vantage prices, dashboard, holdings UI, edit/delete UI | 7
Person 3 | News, Search & Charts News cache, news feed routes, watchlist, allocation chart, news feed UI, stock detail, search UI | 7
All | Shared: Schema design and schema.sql review | 1